## timetable
Week | Due Date | Saturday | What we should finish? | Description&Requirements | Key Points | Other Assignments& Due Date
Week2 |  | 2023-01-14 | 1. First time group meeting 2. Job Position 3. Github& README 4. Research(Inspiration & Resources) 5. PHP-Shell 6. How many pages? 7. What is the name? | Repos and appropriate access / Readme files should be set up. Shell files and project structure should be set up. All team members should have access and be contributing.
Week3 |  | 2023-01-21 | 1. Research Submission 2. HTML & CSS【we should finish one page as the demo】 3.Web wireframe design scheme 4.Practice our presentation on Discord Meeting | In the week four milestone, each group will initiate ideas and concepts for all portions of their campaign to be reviewed by professors. In this stage, teams need to make sure all elements of the project are covered – Website idea(s), Social Media ideas and Marketing & Advertising Solutions. Website structure (NOT the finished app) should be complete in the repository with some initial commits/layout/functionality.
week4 | 2023-01-27 | 2023-01-28 | 1. Presentation in Classtime-5mins 2.submit presentation PDF 3.Github Submit 4. one demo page(first version) 5. one demo video(first version) | Requirements: • Research/rationale must be collected and presented • Online presentation tools can also be used (research your own) • Present initial design work (sketches, logo/wordmark treatments, colours, typography, 17 visuals etc), • These are professional presentations. Prepare accordingly. | Demo should be finished. Structure should be finished. | Jan 15th John-Bee Commercial_Section B
week5 |  | 2023-02-04 |  |  |  | Jan 25th Trevor-FIP Team Page Jan 30th Robert-HW1 - Multi-page PHP Site
week6 |  | 2023-02-11 | 0.improve all works (second version) 1. Improve JS 【We have learned VueJS and use the knowledge from FIP Team Page】 2. Improve PHP 【Before Feb 12th, we have done some PHP homework, which are good for our skills.】 3. Improve Video 4.Improve graphic Design 5.Practice our presentation on Discord Meeting | 1. HTML and CSS can finish 2. JS can create the single application or multiple routers 3. Creates a good database with PHP 4. Video has some good effects. 5.Graphic design almost should be done. | First version of FIP is finished. | Feb 5th Joe-MINI ADVERTISING CAMPAIGN Feb 5th John-Mini Advertising Campaign
week7 |  | 2023-02-18 | 1. Presentation in classtime-10mins 2. submit presentation PDF 3. Github update | The ideas presented in the previous checkpoint are now taking more shape, the students are encouraged to complete as much as possible. At this stage of the project, team ideas and the campaign design direction need to be solidified. Things don’t necessarily have to be fully functioning, but they should be very close to completion. |  | Feb 12th HW2 - PHP Classes Assignment Feb 18th Trevor_ChatAPP
week8 |  | 2023-02-25 | Improve all works | Everthing is almost done. No errors. Only change a very little details. |  | Feb. 19th Raff_Research Assignment I
week9 |  | 2023-03-04
week10 |  | 2023-03-11 | 1.improve 2.practice the presentation | Everthing is done. | Second version of FIP is finished. | Mar.5th Joe-COVER LETTER & RESUME
week11 |  | 2023-03-18 |  |  |  | Mar.12th John-Sports and Data Visualization B Mar.15th John-Title Sequence B Checkpoint
week12 | 2023-03-21 | 2023-03-25 | 1. Presentation in classtime-10mins 2. submit presentation PDF 3. Github update | 100% of everything is done and in working order. Have all of your assets completed and ready to deploy; present your rationale, your creative vision, and your marketing strategy. Tell the story of why and how you came up with your solution and what makes it unique and compelling. |  | Mar. 25th Trevor-ResearchAPP
week13 | 2023-04-02 | 2023-04-02 | FIP Due(final version) | It is a submission time. | Done | Mar. 26th John-Title Sequence B
week14 |  | 2023-04-09 | No FIP and No Classes |  |  | Apr. 6th Robert-Raff-Research Assignment 2
week15 |  | 2023-04-16 | No FIP and No Classes |  |  | Apr.15th Robert-Roku Apr. 16th Raff-Research Assignment 3